## Slide 1: 17 Terawatts to 30 Terawatts – a building perspective
February 2, 2015

## Slide 2: Construction & engineering limitations…
In the past ten years, projects have faced construction and engineering constraints:
  Schedule delays during detailed engineering due to resource limitations
  Significant equipment and materials price increases due demand
  Significant construction cost and schedule impacts due to availability of skilled craft workers
Industry reaction:
  Need to change how a project is executed

## Slide 3: Changes in project execution…
Project execution is faced with changes in resource availability…
  Project scale creates special challenges
  Leverage reduced operating company staff by hiring a separate engineering firms as an “owner’s engineer”
  Detailed design engineering firm needs to execute in multiple offices or in joint ventures/collaborations with other engineering firms
  Use of more expensive/complex modularization to leverage construction labor at fabrication sites around the world
More time and costs for coordination among greater number of sites, companies, etc.

## Slide 4: Exacerbated by “rushing” the planning…
The “gated” design and project development process is very effective when done properly…
The study phase in too many projects has not been completely scoped:
  Long lead equipment not factored into planning
  Construction strategy not part of early planning process
  Incomplete assessment of upcoming EPC market demands
FEED phase design not tailored to modularization approach
Leads to inefficiencies, schedule delays, and costs growth during EPC phase

## Slide 5: It’s all about logistics…
Planning , scoping, and executing a project is all about logistics…
Consider a modern steam cracker complex for the production olefin based chemicals production:
  World scale production of commodity products to achieve economies of scale
  Project will require a significant degree of autonomy, including dedicated systems of utilities and offsites
  Investment likely +/- 10 billions of dollars
  Design complexity needs to address a phased start-up of processing blocks once the utility infrastructure is in place

## Slide 6: It’s all about logistics…
Consider a modern steam cracker complex for the production olefin based chemicals production:
  Construction labor force required for a stick built plant is ~6000 workers – if everything goes well:
    Construction force could peak to ~10,000 to hold schedule:
    Problems due to weather, mobilization difficulties, labor shortages, labor actions, etc, the required labor force could increase further
  For a project of this size, the construction duration may be 2 years to 3+ years
  In many regions of North America, there are not sufficient numbers of trained craft workers within hundreds of miles of the project site:
    And, most are already employed by other companies

## Slide 7: And, there are mobilization realities…
Consider a workforce of 6000 craft workers:
  The logistics to just transport these workers from the parking lot, through Security, and to the job site every day is considerable
  Short-term housing is required whether the job site is in Lake Charles or Houston – or Riyadh
  Food and other amenities are needed
  First aid and medical facilities are a necessity
  Schools for children of the craft force may be needed as well
  All this needs to be in the project budget
Many workers will come from other States:
  Many may need specific training for the project, for example, welding of special alloy piping…

## Slide 8: And, there are mobilization realities…
Consider a workforce of ~6000 craft workers:
  All of these workers are busy in one site which may only be 400 acres in size
  Construction interferences – equipment, other crafts, other workers – will impact productivity
  Areas need to be cleared of personnel for safety reasons during large lifts by crane or welding above grade
  To relieve this congestion – and shortage of local craft workers – modularization or pre-assembly will be used

## Slide 9: Disperse the workforce…
Modularization/pre-assembly is now a common feature of most mega projects:
  Build modules away from the project location to relieve congestion
  Build modules where there are more skilled craft workers
  Build indoors or in milder climates where weather delays are not a factor
  Create module fabrication facilities that can be base loaded versus the temporary work site:
    Implement more automation into fabrication than may be possible at the project site
  Minimize the size of the local workforce at the project site to minimize the disruption to the community

## Slide 10: Engineering bottlenecks with mega projects…
The same applies to detailed engineering and procurement:
  Rarely is a mega project executed in one office location of by a single EPC firm
  No one office has the scale to handle a mega project anymore
  And, startup and completion of a mega project is very disruptive to staffing
  The financial risk is onerous for a single company

## Slide 11: Looking ahead…
The gated approach – multiple studies, followed by a single FEED effort, and then detailed engineering and procurement – is the best method to develop any project:
  Take the time to plan early – before hiring large teams
  Develop the procurement and construction execution strategy early – in the study phases
  Include courses in gated execution in project management and construction curricula

## Slide 12: Looking ahead…
Grow the craft work force:
  Centralized fabrication sites can provide employment stability
  Specific training for the project at hand
  Greatest challenge to attract and hold craft workers is pay:
    Over the past 40 years, craft wage rates have been flat or declining in real dollars

## Slide 13: Looking ahead…
New technology will have the greatest impact:
  Consider friction stir welding for repetitive welding:
    Better quality than fusion welding
    ~100% repeatability
    Better weld properties
    Possible to assess weld quality as it is done
    No worker exposure to metals fumes
  Weld inspection techniques:
    More thorough examination
    Faster assessments
Technology needs to offset the challenges of a declining workforce